## Detailed Schedule
| Information |  |  |  | Hours Multiplier: | 1.3 | PERT Analysis |  |  |  |  | Starter Task | No slack (Critical Path)
| No/meaningless value | [5 empty] | Expected Hours: | 345.8 |  |  |  | Final Task (Critical path)
| Calculated value | [5 empty] | Standard Deviation: | 68.4667
Input/manual entry
[5 empty] | Labor Hours |  |  | Schedule Hours |  |  | PERT Average (Rounded Up) | Activity Tables
Task |  | Description | Required Skills | Prerequisites | Optimistic Hours | Normal Hours | Pessimistic Hours | Optimistic Hours | Normal Hours | Pessimistic Hours |  | Early Start | Early Finish | Late Start | Late Finish | Slack
1 GUI |  | The visual representation and editor of the project data. It will contain a General Pane, a Requirements Pane, and an Hour Log Pane | JavaFX |  | 68 | 150 | 263 | 88.4 | 195 | 341.9 | 202 | -- | #VALUE! | -202
1.1 General Page |  | A pane to display the current team, the project description, the project manager, and the risks involved in the project | JavaFX |  | 23 | 54 | 107 | 29.9 | 70.2 | 139.1 | 75 | -- | #VALUE! | -75
1.1.1 Description Panel |  | Displays and edits the description of the project | JavaFX |  | 2 | 4 | 9 | 2.6 | 5.2 | 11.7 | 6 | -- | #VALUE! | -6
1.1.1.1 Display Description |  | Display the description in an editable textbox. If the description is changed, indicate that it has been adjusted. Remove the indicator once the changes have been saved | JavaFX | 2.8 | 1 | 2 | 5 | 1.3 | 2.6 | 6.5 | 4 | 34 | 38 | 46 | 50 | 12
1.1.1.2 Edit Description |  | Allow the user to update the description by typing in and editing the textbox. Allow the changes to be saved or reverted | JavaFX | 1.1.1.1 | 1 | 2 | 4 | 1.3 | 2.6 | 5.2 | 3 | 38 | 41 | 50 | 53 | 12
1.1.2 Manager Panel |  | Allow the user to select a team member to be made manager. Setting a new person as manager will remove the old manager from the position. Team members will be displayed in a scrollpane as a list of buttons. | JavaFX |  | 2 | 7 | 14 | 2.6 | 9.1 | 18.2 | 10 | -- | #VALUE! | -10 |  | #VALUE!
1.1.2.1 Display Manager |  | Indicate which team member is manager by printing their name at the top of the pane and highlighting the button of the appropriate person | JavaFX | 1.9, 2.7 | 1 | 5 | 10 | 1.3 | 6.5 | 13 | 7 | 29 | 36 | 43 | 50 | 14
1.1.2.2 Edit Manager |  | Select a new manager by clicking the button with the person's name on it, and selecting "yes" on the confirmation pop-up window. | JavaFX | 1.1.2.1 | 1 | 2 | 4 | 1.3 | 2.6 | 5.2 | 3 | 36 | 39 | 50 | 53 | 14
1.1.3 Members Panel |  | Displays and edits the members of the project team | JavaFX |  | 11 | 24 | 53 | 14.3 | 31.2 | 68.9 | 35 | -- | #VALUE! | -35 |  | #VALUE!
1.1.3.1 Display Team Members |  | Display the team members in a list of buttons in a scrollpane | JavaFX | 1.9, 2.7 | 3 | 5 | 10 | 3.9 | 6.5 | 13 | 8 | 29 | 37 | 29 | 37 | 0
1.1.3.2 Add Team Member |  | Click a button that prompts the user to add a new member by name | JavaFX | 1.1.3.1 | 1 | 4 | 8 | 1.3 | 5.2 | 10.4 | 6 | 37 | 43 | 37 | 43 | 0
1.1.3.3 Edit Team Members |  | Click the button of the corresponding team member to edit their information | JavaFX | 1.1.3.2 | 1 | 4 | 10 | 1.3 | 5.2 | 13 | 6 | 43 | 49 | 47 | 53 | 4
1.1.3.4 Display Team Member's WorkedHours |  | Click the button of the corresponding team member to display their reported hours | JavaFX | 1.1.3.2 | 3 | 6 | 15 | 3.9 | 7.8 | 19.5 | 10 | 43 | 53 | 43 | 53 | 0
1.1.3.5 Delete Team Member |  | Click the button of the corresponding team member to prompt the user to delete the member | JavaFX | 1.1.3.2 | 3 | 5 | 10 | 3.9 | 6.5 | 13 | 8 | 43 | 51 | 45 | 53 | 2
1.1.4 Risks Panel |  | Displays and edits the risks of the project | JavaFX |  | 8 | 19 | 31 | 10.4 | 24.7 | 40.3 | 25 | -- | #VALUE! | -25 |  | #VALUE!
1.1.4.1 Display Risks |  | Display the risks in a scrollpane which shows a short description of the risk, the percentage likelihood that the issue may occur, and the dollar amount associated with correcting the risk | JavaFX | 2.6 | 3 | 10 | 15 | 3.9 | 13 | 19.5 | 13 | 9 | 22 | 29 | 42 | 20
1.1.4.2 Add Risk |  | Click a button that prompts the user to add a new risk by description, percentage likelihood, and recovery cost | JavaFX | 1.1.4.1 | 2 | 4 | 8 | 2.6 | 5.2 | 10.4 | 6 | 22 | 28 | 42 | 48 | 20
1.1.4.3 Edit Risk |  | Click the appropriate risk (label? Button?) to display a pop-up window that allows the risk to be edited | JavaFX | 1.1.4.2 | 2 | 3 | 5 | 2.6 | 3.9 | 6.5 | 5 | 28 | 33 | 48 | 53 | 20
1.1.4.4 Delete Risk |  | Click the appropriate risk to display a pop-up window that prompts the user to delete the risk | JavaFX | 1.1.4.2 | 1 | 2 | 3 | 1.3 | 2.6 | 3.9 | 3 | 28 | 31 | 50 | 53 | 22
1.2 Requirements Page |  | Displays and edits the project requirements | JavaFX |  | 11 | 26 | 34 | 14.3 | 33.8 | 44.2 | 33 | -- | #VALUE! | -33 |  | #VALUE!
1.2.1 Display Requirements |  | Displays the requirements by item number, description, source, priority, acceptance status, and completion status | JavaFX | 2.5 | 4 | 12 | 15 | 5.2 | 15.6 | 19.5 | 15 | 12 | 27 | 22 | 37 | 10
1.2.2 Add Requirements |  | Allows the user to add requirements based on a description, source, priority, acceptance status, and completion status | JavaFX | 1.2.1 | 4 | 8 | 10 | 5.2 | 10.4 | 13 | 10 | 27 | 37 | 37 | 47 | 10
1.2.3 Edit Requirements (Including to mark complete?) |  | Click the requirement (label?) to display a pop-up that allows the user to edit its information | JavaFX | 1.2.2 | 2 | 4 | 6 | 2.6 | 5.2 | 7.8 | 6 | 37 | 43 | 47 | 53 | 10
1.2.3 Delete Requirements |  | Click the requirement (label?) to display a pop-up that prompts the user to delete the requirement | JavaFX | 1.2.2 | 1 | 2 | 3 | 1.3 | 2.6 | 3.9 | 3 | 37 | 40 | 50 | 53 | 13
1.3 Hour Log Pane |  | Displays the project hourlog distribution by activity, and allows new hours to be logged based on a daily orweekly submission timetable | JavaFX |  | 7 | 18 | 33 | 9.1 | 23.4 | 42.9 | 25 | -- | #VALUE! | -25 |  | #VALUE!
1.3.1 Display expended WorkedHours |  | Displays the distribution of worked hours by activity (i.e. requirements, designing, coding, etc.) | JavaFX |  | 4 | 9 | 18 | 5.2 | 11.7 | 23.4 | 13 | -- | #VALUE! | -13 |  | #VALUE!
1.3.1.1 Display Total WorkedHours |  | Displays the total worked hours for the project. This will be printed as a value above where the hours of each type are listed | JavaFX | 2.1.1, 2.1.2, 2.2 | 2 | 4 | 8 | 2.6 | 5.2 | 10.4 | 6 | 23 | 29 | 40 | 46 | 17
1.3.1.2 Display hours by WorkedHourType |  | Displays the how many hours of each type have been worked. This displays the value, as well as a progress bar that shows the percentage of hours by type divided by the total hours | JavaFX | 1.3.1.1 | 2 | 5 | 10 | 2.6 | 6.5 | 13 | 7 | 29 | 36 | 46 | 53 | 17
1.3.2 Submit new WorkedHours |  | Allows the user to edit some fields to create a new WorkedHours for submission. Will catch and handle errors thrown by the WorkedHours constructor when invalid WorkedHourTypes are used. The user will select the submitting member via a PersonButtonScrollPane, which will display the person's name and ID in the submission form. Then the user will be allowed to complete the form by specifying the type of work done and the duration. | JavaFX |  | 3 | 9 | 15 | 3.9 | 11.7 | 19.5 | 12 | -- | #VALUE! | -12 |  | #VALUE!
1.3.2.1 Force by schedule standards (day or week) |  | Allows the user to select a standard time-frame for WorkedHours submission. This can either be done on the first overall submission of WorkedHours for a Project, or can be done in the Settings window. After this, if the user attempts to switch timeframes, an error is displayed (?) | JavaFX | 2.1, 2.2 | 1 | 5 | 7 | 1.3 | 6.5 | 9.1 | 7 | 23 | 30 | 40 | 47 | 17
1.3.2.2 Add effort by contributing Person and WorkedHourType |  | Use the entered data to push a new WorkedHour submission to the Team, which will register it in the ProjectHourLog | JavaFX | 1.3.2.1 | 2 | 4 | 8 | 2.6 | 5.2 | 10.4 | 6 | 30 | 36 | 47 | 53 | 17
1.4 Help Page |  | Used to display helpful information to the user | JavaFX |  | 5 | 10 | 18 | 6.5 | 13 | 23.4 | 14 | -- | #VALUE! | -14 |  | #VALUE!
1.4.1 Pop-up Stage |  | Will use the PopupStage library added to this project | JavaFX | -- | 2 | 5 | 10 | 2.6 | 6.5 | 13 | 7 | 0 | 7 | 39 | 46 | 39
1.4.2 Display helpful information |  | Will display helpful information like "Contact us if you need help"???? | JavaFX | 1.4.1 | 3 | 5 | 8 | 3.9 | 6.5 | 10.4 | 7 | 7 | 14 | 46 | 53 | 39
1.5 About Page |  | Will display information about us | JavaFX |  | 3 | 5 | 9 | 3.9 | 6.5 | 11.7 | 7 | -- | #VALUE! | -7 |  | #VALUE!
1.5.1 Pop-up Stage |  | Will use the PopupStage library added to this project | JavaFX | -- | 2 | 3 | 5 | 2.6 | 3.9 | 6.5 | 5 | 0 | 5 | 45 | 50 | 45
1.5.2 Display information about us! :D |  | Will provide an email to contact???? | JavaFX | 1.5.1 | 1 | 2 | 4 | 1.3 | 2.6 | 5.2 | 3 | 5 | 8 | 50 | 53 | 45
1.6 Settings Page |  | Will allow the user to edit information about how the GUI handles the Project | JavaFX |  | 7 | 18 | 35 | 9.1 | 23.4 | 45.5 | 25 | -- | #VALUE! | -25 |  | #VALUE!
1.6.1 Pop-up Stage |  | Will use the PopupStage library added to this project | JavaFX | -- | 3 | 10 | 20 | 3.9 | 13 | 26 | 14 | 0 | 14 | 26 | 40 | 26
1.6.2 Allow settings to be changed |  | Certain settings can only be changed on initialization of the project, and will be locked in once the first submissions are made. There will need to be hover-text or a pop-up that says this | JavaFX | 1.6.1 | 1 | 2 | 5 | 1.3 | 2.6 | 6.5 | 4 | 14 | 18 | 40 | 44 | 26
1.6.3 Settings for: |  | Settings will include the Day/Week standard, ...... | JavaFX |  | 3 | 6 | 10 | 3.9 | 7.8 | 13 | 9 | -- | #VALUE! | -9 |  | #VALUE!
1.6.3.1 Day/Week standard |  | Will force the user to maintain the Day/Week standard they adopted for the project. If they attempt to submit by a different standard, an error will be displayed | JavaFX | 1.6.2, 2.2.2 | 3 | 6 | 10 | 3.9 | 7.8 | 13 | 9 | 18 | 27 | 44 | 53 | 26
1.7 Load/Save Pages |  | Will allow the user to save the current project or load a new one | JavaFX |  | 7 | 11 | 15 | 9.1 | 14.3 | 19.5 | 15 | -- | #VALUE! | -15 |  | #VALUE!
1.7.1 Pop-up Stage |  | This will use the FileChooser library from the Java standard library | JavaFX | -- | 2 | 3 | 4 | 2.6 | 3.9 | 5.2 | 4 | 0 | 4 | 45 | 49 | 45
1.7.2 If loading or exiting, prompt user to save first |  | If the current project is about to be discarded, prompt the user to save first | JavaFX | 1.7.1, 2.8.5 | 2 | 3 | 4 | 2.6 | 3.9 | 5.2 | 4 | 34 | 38 | 49 | 53 | 15
1.7.3 Save |  | On first “Save” or “Save As”, prompt user to specify file name/location. On subsequent uses of “Save”, use that location and filename (persist across opening/closing of GUI) | JavaFX | 1.7.4, 2.8.4 | 2 | 3 | 4 | 2.6 | 3.9 | 5.2 | 4 | 33 | 37 | 49 | 53 | 16
1.7.4 Save As |  | On “Save As”, save as the specified filename/location each time | JavaFX | 1.7.1, 2.8.4 | 1 | 2 | 3 | 1.3 | 2.6 | 3.9 | 3 | 30 | 33 | 50 | 53 | 20
1.8 PersonButton |  | A Button that holds an instance of a Person, and displays their name. Different actions can be provided, so that it can fill the needed requirements of the TeamMembersPane, ManagerPane, and the TeamPane on the HourLog pane | JavaFX, Inheritance | 2.1.2.1 | 2 | 3 | 4 | 2.6 | 3.9 | 5.2 | 4 | 3 | 7 | 18 | 22 | 15
1.9 PersonButtonScrollPane |  | A scrollpane specifically made to handle PersonButtons. Can handle the buttons by either Person or by PersonButton. If just a Person is used, it either locates the button that holds it, or will create a new button for that Person | JavaFX, Inheritance | 1.8 | 3 | 5 | 8 | 3.9 | 6.5 | 10.4 | 7 | 7 | 14 | 22 | 29 | 15
2 Back-end System |  | The internal mechanics that make the GUI work |  |  | 56 | 108 | 177 | 72.8 | 140.4 | 230.1 | 145 | -- | #VALUE! | -145 |  | #VALUE!
2.1 Team organization |  | All classes pertaining to the team, including the Team.class, Person.class, and the HourLog package |  |  | 18 | 27 | 36 | 23.4 | 35.1 | 46.8 | 36 | -- | #VALUE! | -36 |  | #VALUE!
2.1.1 Team class |  | A class used to represent and act as a team. It holds the Person team members, can identify the manager, and should handle most interactions between the Team package and outside classes |  |  | 11 | 16 | 21 | 14.3 | 20.8 | 27.3 | 21 | -- | #VALUE! | -21 |  | #VALUE!
2.1.1.1 Add Person instances |  | Adds a new Person to the team |  | 2.1.2.1 | 2 | 3 | 4 | 2.6 | 3.9 | 5.2 | 4 | 3 | 7 | 9 | 13 | 6
2.1.1.2 Remove Person instances |  | Removes the Person from the team. If the Person is still represented in the HourLog as a contributor, the instance will not be removed from memory, though the Person will no longer be directly accessible |  | 2.1.1.1 | 3 | 4 | 5 | 3.9 | 5.2 | 6.5 | 6 | 7 | 13 | 13 | 19 | 6
2.1.1.3 Provide Total Team WorkedHours |  | Provide a way for outside classes to get information from the HourLog via the Team class |  | 2.2.1.2.1 | 2 | 3 | 4 | 2.6 | 3.9 | 5.2 | 4 | 18 | 22 | 19 | 23 | 1
2.1.1.4 Provide Team WorkedHours for given WorkedHourType |  | Provide a way for outside classes to get information from the HourLog via the Team class |  | 2.1.2.1, 2.2.1.2.1 | 2 | 3 | 4 | 2.6 | 3.9 | 5.2 | 4 | 18 | 22 | 19 | 23 | 1
2.1.1.5 Provide Team WorkedHours for given Person |  | Provide a way for outside classes to get information from the HourLog via the Team class |  | 2.1.2, 2.2.1.2.2 | 2 | 3 | 4 | 2.6 | 3.9 | 5.2 | 4 | 19 | 23 | 19 | 23 | 0
2.1.2 Person class |  | A class to represent a member on a Team |  |  | 7 | 11 | 15 | 9.1 | 14.3 | 19.5 | 15 | -- | #VALUE! | -15 |  | #VALUE!
2.1.2.1 Person data |  | Holds the person's name, a unique ID (for people with the same name), and whether or not the person is a manager. Reports hours to the Team, which registers it in the HourLog |  | -- | 1 | 2 | 3 | 1.3 | 2.6 | 3.9 | 3 | 0 | 3 | 6 | 9 | 6
2.1.2.2 Report WorkedHours to ProjectWorkedHours |  | Reports hours to the Team. (Throw exception if submission is not in accordance with Weekly/Daily timeframe?) |  | 2.1.1, 2.2.1.1 | 2 | 3 | 4 | 2.6 | 3.9 | 5.2 | 4 | 15 | 19 | 19 | 23 | 4
2.1.2.3 Promote to Manager |  | Promotes the Person to a Manager |  | 2.1.2.1 | 2 | 3 | 4 | 2.6 | 3.9 | 5.2 | 4 | 3 | 7 | 49 | 53 | 46
2.1.2.4 Demote to Programmer |  | Demotes this Person from Manager |  | 2.1.2.1 | 2 | 3 | 4 | 2.6 | 3.9 | 5.2 | 4 | 3 | 7 | 49 | 53 | 46
2.2 Hour Log |  | Keeps track of the submitted hours, and provides information on how many hours certain members have worked, or how many hours have been worked on a certain type of job type (i.e. requirements, designing, etc.) |  |  | 9 | 19 | 31 | 11.7 | 24.7 | 40.3 | 26 | -- | #VALUE! | -26 |  | #VALUE!
2.2.1 ProjectHourLog class |  | Stores WorkedHour instances, and retrieves them based on specified parameters |  |  | 7 | 14 | 22 | 9.1 | 18.2 | 28.6 | 19 | -- | #VALUE! | -19 |  | #VALUE!
2.2.1.1 Stores all WorkedHours instances for the project |  | Store them in the order they are submitted. Do not worry about sorting |  | 2.2.2 | 3 | 5 | 7 | 3.9 | 6.5 | 9.1 | 7 | 8 | 15 | 9 | 16 | 1
2.2.1.2 Can provide WorkedHours sum of |  | Retrieves the number of hours worked by the below parameters |  |  | 4 | 9 | 15 | 5.2 | 11.7 | 19.5 | 12 | -- | #VALUE! | -12 |  | #VALUE!
2.2.1.2.1 WorkedHourType |  | Retrieves the number of hours worked by the given WorkedHourType |  | 2.2.1.1, 2.2.3 | 1 | 2 | 3 | 1.3 | 2.6 | 3.9 | 3 | 15 | 18 | 16 | 19 | 1
2.2.1.2.2 Person |  | Retrieves the number of hours worked by the given Person |  | 2.2.1.1, 2.1.2.1 | 1 | 2 | 3 | 1.3 | 2.6 | 3.9 | 3 | 15 | 18 | 16 | 19 | 1
2.2.2 WorkedHours class |  | Records who worked what number of hours for a given time period, and what type of work they were doing |  | 2.2.3 | 1 | 4 | 8 | 1.3 | 5.2 | 10.4 | 6 | 2 | 8 | 3 | 9 | 1
2.2.3 WorkedHourType enum |  | Any - Requirements - Design - Coding - Testing - Project_Management |  | -- | 1 | 1 | 1 | 1.3 | 1.3 | 1.3 | 2 | 0 | 2 | 1 | 3 | 1
2.3 Load/Save Configuration |  | Load/save the GUI/Project configuration | File Input/Output Steams |  | 9 | 19 | 27 | 11.7 | 24.7 | 35.1 | 25 | -- | #VALUE! | -25 |  | #VALUE!
2.3.1 Initialize new config file if none present |  | Creates a new config file, and loads it with the default settings | File | -- | 2 | 4 | 5 | 2.6 | 5.2 | 6.5 | 5 | 0 | 5 | 32 | 37 | 32
2.3.2 Read configuration from config file |  | Reads the settings from an existing config file | Scanner | 2.3.3 | 2 | 3 | 4 | 2.6 | 3.9 | 5.2 | 4 | 21 | 25 | 49 | 53 | 28
2.3.3 Save configuration |  | Saves the current configuration to the config file |  |  | 5 | 12 | 18 | 6.5 | 15.6 | 23.4 | 16 | -- | #VALUE! | -16 |  | #VALUE!
2.3.3.1 Save Configuration |  | Writes the current configuration to the file | FileOutputStream | 2.3.1 | 1 | 4 | 6 | 1.3 | 5.2 | 7.8 | 5 | 5 | 10 | 37 | 42 | 32
2.3.3.2 Do not lose information from current file |  | Ensure that any other text is not overwritten (i.e. just replace old values with the new ones) |  | 2.3.3.1 | 4 | 8 | 12 | 5.2 | 10.4 | 15.6 | 11 | 10 | 21 | 42 | 53 | 32
2.4 Logging |  | Output descriptive status updates to the log | FileOutputStream |  | 5 | 13 | 33 | 6.5 | 16.9 | 42.9 | 20 | -- | #VALUE! | -20 |  | #VALUE!
2.4.1 Print updates to log w/ timestamp |  | Print out the status message with a date/time token in front to indicate when the message was printed |  | -- | 3 | 5 | 10 | 3.9 | 6.5 | 13 | 8 | 0 | 8 | 37 | 45 | 37
2.4.2 Redirect System.out and System.err to log |  | Redirect System.out and System.err to the log so that any crash messages or other messages using the System printstream will be displayed in the log |  | 2.4.1 | 1 | 5 | 15 | 1.3 | 6.5 | 19.5 | 8 | 8 | 16 | 45 | 53 | 37
2.4.3 Clear old logs to prevent build-up |  | Make sure that log files do not build up beyond a certain limit, probably 5 |  | -- | 1 | 3 | 8 | 1.3 | 3.9 | 10.4 | 5 | 0 | 5 | 48 | 53 | 48
2.5 Requirements |  | Store the requirements and requirement data |  | -- | 6 | 10 | 14 | 7.8 | 13 | 18.2 | 13 | -- | #VALUE! | -13 |  | #VALUE!
2.5.1 Requirement class |  | Store the requirement data. Specifically, the Source, description, item number, acceptance status, completion status, and priority |  | 2.5.3, 2.5.4, 2.5.5 | 1 | 3 | 5 | 1.3 | 3.9 | 6.5 | 4 | 2 | 6 | 15 | 19 | 13
2.5.2 RequirementsList |  | Store all of the requirements. Also retrieves a separate list of requirements based on a parameter, such as Priority level or Acceptance status | Inheritance |  | 5 | 7 | 9 | 6.5 | 9.1 | 11.7 | 10 | -- | #VALUE! | -10 |  | #VALUE!
2.5.2.1 Extend LinkedList<Requirement> |  |  |  | 2.5.1 | 1 | 2 | 3 | 1.3 | 2.6 | 3.9 | 3 | 6 | 9 | 19 | 22 | 13
2.5.2.2 Return Requirements based on parameter |  |  |  | 2.5.2.1 | 1 | 2 | 3 | 1.3 | 2.6 | 3.9 | 3 | 9 | 12 | 50 | 53 | 41
2.5.3 Priority Enum |  | Unassigned - Critical - High - Medium - Low |  | -- | 1 | 1 | 1 | 1.3 | 1.3 | 1.3 | 2 | 0 | 2 | 13 | 15 | 13
2.5.4 Status Enum |  | Pending_Consideration - Accepted_Current - Accepted_Post_Release - Rejected |  | -- | 1 | 1 | 1 | 1.3 | 1.3 | 1.3 | 2 | 0 | 2 | 13 | 15 | 13
2.5.5 Completion Status Enum |  | Not_Started - In_Progress - Awaiting_QA - Completed |  | -- | 1 | 1 | 1 | 1.3 | 1.3 | 1.3 | 2 | 0 | 2 | 13 | 15 | 13
2.6 Risks |  |  |  |  | 2 | 5 | 11 | 2.6 | 6.5 | 14.3 | 8 | -- | #VALUE! | -8 |  | #VALUE!
2.6.1 Risk class |  |  |  | -- | 1 | 3 | 6 | 1.3 | 3.9 | 7.8 | 5 | 0 | 5 | 33 | 38 | 33
2.6.2 RiskList class |  |  |  | 2.6.1 | 1 | 2 | 5 | 1.3 | 2.6 | 6.5 | 4 | 5 | 9 | 38 | 42 | 33
2.7 TeamPresenter interface |  | An interface used by JavaFX objects that display the Team and its members. Specifies methods AddMember, RemoveMember, and UpdateTeam |  | 2.1 | 2 | 4 | 6 | 2.6 | 5.2 | 7.8 | 6 | 23 | 29 | 23 | 29 | 0
2.8 Project class |  |  |  |  | 5 | 11 | 19 | 6.5 | 14.3 | 24.7 | 15 | -- | #VALUE! | -15 |  | #VALUE!
2.8.1 Initialize empty Team |  |  |  | 2.1.1 | 1 | 2 | 3 | 1.3 | 2.6 | 3.9 | 3 | 23 | 26 | 42 | 45 | 19
2.8.2 Intialize new RequirementsList |  |  |  | 2.5.2 | 1 | 2 | 3 | 1.3 | 2.6 | 3.9 | 3 | 12 | 15 | 42 | 45 | 30
2.8.3 Initialize new RisksList |  |  |  | 2.6.2 | 1 | 2 | 3 | 1.3 | 2.6 | 3.9 | 3 | 9 | 12 | 42 | 45 | 33
2.8.4 Save current Project |  |  | File Input/Output Steams | 2.8.1, 2.8.2, 2.8.3 | 1 | 2 | 5 | 1.3 | 2.6 | 6.5 | 4 | 26 | 30 | 45 | 49 | 19
2.8.5 Load saved Project from file |  |  | File Input/Output Steams | 2.5.4 | 1 | 3 | 5 | 1.3 | 3.9 | 6.5 | 4 | 30 | 34 | 45 | 49 | 15
|  |  |  | Totals: | 124 | 258 | 440 | 161.2 | 335.4 | 572 |  | MAX: | 53

## Scheduling Assignments
Scheduling Assignments
Hour | Mark | Nygel | Lauren | Sharmell | Bilash
0 | 2.2.3 | 2.1.2.1 | 2.5.3 | 2.5.4 | 2.4.3
1
2 | 2.2.2 |  | 2.5.5
3 |  | 2.1.2.3
4 |  |  | 2.1.1.1 | 2.5.1
5 |  |  |  |  | 2.6.1
6
7 |  | 2.1.2.4
8 | 2.2.1.1 |  | 2.1.1.2 | 2.5.2.1
9
10 |  |  |  |  | 2.6.2
11 |  | 1.8 |  | 2.5.2.2
12
13
14 |  |  |  | 2.8.2 | 2.8.3
15 | 2.1.2.2 | 2.2.1.2.1 | 2.2.1.2.2
16
17 |  |  |  | 1.9 | 2.4.1
18 |  | 2.1.1.3 | 2.1.1.4
19 | 2.1.1.5
20
21
22 |  |  | 1.7.1
23 | 2.7 | 1.3.1.1
24 |  |  |  | 1.2.1
25 |  |  |  |  | 2.4.2
26 |  |  | 1.3.2.1
27
28
29 |  | 1.3.1.2
30 | 1.1.3.1
31
32
33 |  |  | 1.3.2.2 |  | 2.8.1
34
35
36 |  | 1.1.2.1 |  |  | 2.8.4
37
38 | 1.1.3.2
39 |  |  | 1.4.1 | 1.2.2
40 |  |  |  |  | 1.6.1
41
42
43 |  | 2.3.1
44 | 1.1.3.4
45
46 |  |  | 1.1.3.5
47
48 |  | 2.3.3.1
49 |  |  |  | 1.1.4.1
50
51
52
53 |  | 2.3.3.2
54 | 2.8.5 |  | 1.5.1 |  | 1.6.2
55
56
57
58 | 1.1.1.1 |  |  |  | 1.6.3.1
59 |  |  | 1.7.4
60
61
62 | 1.1.1.2 |  | 1.7.3 | 1.1.4.2
63
64 |  | 2.3.2
65 | 1.2.3
66 |  |  | 1.1.2.2
67 |  |  |  |  | 1.7.2
68 |  | 1.4.2
69 |  |  | 1.1.3.3 | 1.1.4.3
70
71 | 1.1.4.4
72
73
74