## High-Level Schedule
Task | Labor Hours | Schedule Hours
1 GUI | 25 | 32.5
1.1 General Page | 9 | 11.7
1.1.1 Description Panel | 1 | 1.3
1.1.1.1 Display Description |  | 0
1.1.1.2 Edit Description |  | 0
1.1.2 Manager Panel | 3 | 3.9
1.1.2.1 Display Manager |  | 0
1.1.2.2 Edit Manager |  | 0
1.1.2.2.1 Create new Manager |  | 0
1.1.2.2.2 Promote Team Member to Manager |  | 0
1.1.3 Members Panel | 3 | 3.9
1.1.3.1 Display Team Members |  | 0
1.1.3.2 Add Team Member |  | 0
1.1.3.3 Edit Team Members |  | 0
1.1.3.4 Display Team Members Effort |  | 0
1.1.3.5 Delete Team Member (just archives them) |  | 0
1.1.4 Risks Panel | 2 | 2.6
1.1.4.1 Display Risks |  | 0
1.1.4.2 Add Risk |  | 0
1.1.4.3 Edit Risk |  | 0
1.1.4.4 Delete Risk |  | 0
1.2 Requirements Page | 4 | 5.2
1.2.1 Display Requirements | 1 | 1.3
1.2.2 Edit Requirements (Including to mark complete?) | 2 | 2.6
1.2.3 Delete Requirements | 1 | 1.3
1.3 Effort Tracking and Monitoring Page | 2 | 2.6
1.3.1 Display expended Effort | 2 | 2.6
1.3.1.1 Display Total Effort |  | 0
1.3.1.2 Display effort by EffortType |  | 0
1.3.2 Submit new Effort | 2 | 2.6
1.3.2.1 Force by schedule standards (day or week) |  | 0
1.3.2.2 Add effort by contributing Person and EffortType |  | 0
1.4 Help Page | 2 | 2.6
1.4.1 Pop-up Stage |  | 0
1.5 About Page | 1 | 1.3
1.5.1 Pop-up Stage |  | 0
1.5.2 Display information about us! :D |  | 0
1.6 Settings Page | 3 | 3.9
1.6.1 Pop-up Stage |  | 0
1.6.2 Settings for: |  | 0
1.6.2.1 Day/Week standard |  | 0
1.6.2.2 # of Managers |  | 0
1.6.2.3 |  | 0
1.7 Load/Save Pages | 4 | 5.2
1.7.1 Pop-up Stage |  | 0
1.7.2 If loading, prompt user to save first |  | 0
1.7.3 On first “Save” or “Save As”, prompt user to specify file name/location. On subsequent uses of “Save”, use that location and filename (persist across opening/closing of GUI) |  | 0
1.7.4 On “Save As”, save as the specified filename/location each time |  | 0
2 Back-end System | 12.1 | 15.73
2.1 Team organization | 6 | 7.8
2.1.1 Team class | 3 | 3.9
2.1.1.1 Add Person instances |  | 0
2.1.1.2 Remove Person instances |  | 0
2.1.1.3 Provide Total Team Effort |  | 0
2.1.1.4 Provide Team Effort for given EffortType |  | 0
2.1.2 Person abstract class | 1 | 1.3
2.1.2.1 Report Effort to ProjectEffort |  | 0
2.1.3 Programmer class | 1 | 1.3
2.1.3.1 Promote to Manager |  | 0
2.1.4 Manager class | 1 | 1.3
2.4.1.1 Demote to Programmer |  | 0
2.2 Effort Monitoring and Tracking System | 4.1 | 5.33
2.2.1 ProjectEffort class | 3 | 3.9
2.2.1.1 Stores all Effort instances for the project |  | 0
2.2.1.2 Can provide List<Effort> of |  | 0
2.2.2 Effort class | 1 | 1.3
2.2.3 EffortType enum | 0.1 | 0.13
2.3 Load/Save Status | 2 | 2.6
TOTAL | 37.1 | 48.23

## Detailed Schedule
Task | Labor Hours | Schedule Hours
1 GUI | 53 | 68.9
1.1 General Page | 22 | 28.6 | Calculated Value
1.1.1 Description Panel | 2 | 2.6 | Base Value
1.1.1.1 Display Description | 1 | 1.3
1.1.1.2 Edit Description | 1 | 1.3
1.1.2 Manager Panel | 1 | 1.3
1.1.2.1 Display Manager | 1 | 1.3
1.1.2.2 Edit Manager | 4 | 5.2
1.1.2.2.1 Create new Manager | 2 | 2.6
1.1.2.2.2 Promote Team Member to Manager | 2 | 2.6
1.1.3 Members Panel | 11 | 14.3
1.1.3.1 Display Team Members | 3 | 3.9
1.1.3.2 Add Team Member | 1 | 1.3
1.1.3.3 Edit Team Members | 1 | 1.3
1.1.3.4 Display Team Members Effort | 3 | 3.9
1.1.3.5 Delete Team Member (just archives them) | 3 | 3.9
1.1.4 Risks Panel | 8 | 10.4
1.1.4.1 Display Risks | 3 | 3.9
1.1.4.2 Add Risk | 2 | 2.6
1.1.4.3 Edit Risk | 2 | 2.6
1.1.4.4 Delete Risk | 1 | 1.3
1.2 Requirements Page | 4 | 5.2
1.2.1 Display Requirements | 1 | 1.3
1.2.2 Edit Requirements (Including to mark complete?) | 2 | 2.6
1.2.3 Delete Requirements | 1 | 1.3
1.3 Effort Tracking and Monitoring Page | 7 | 9.1
1.3.1 Display expended Effort | 4 | 5.2
1.3.1.1 Display Total Effort | 2 | 2.6
1.3.1.2 Display effort by EffortType | 2 | 2.6
1.3.2 Submit new Effort | 3 | 3.9
1.3.2.1 Force by schedule standards (day or week) | 1 | 1.3
1.3.2.2 Add effort by contributing Person and EffortType | 2 | 2.6
1.4 Help Page | 2 | 2.6
1.4.1 Pop-up Stage | 2 | 2.6
1.5 About Page | 3 | 3.9
1.5.1 Pop-up Stage | 2 | 2.6
1.5.2 Display information about us! :D | 1 | 1.3
1.6 Settings Page | 8 | 10.4
1.6.1 Pop-up Stage | 3 | 3.9
1.6.2 Settings for: | 5 | 6.5
1.6.2.1 Day/Week standard | 3 | 3.9
1.6.2.2 # of Managers | 2 | 2.6
1.6.2.3 |  | 0
1.7 Load/Save Pages | 7 | 9.1
1.7.1 Pop-up Stage | 2 | 2.6
1.7.2 If loading, prompt user to save first | 2 | 2.6
1.7.3 On first “Save” or “Save As”, prompt user to specify file name/location. On subsequent uses of “Save”, use that location and filename (persist across opening/closing of GUI) | 2 | 2.6
1.7.4 On “Save As”, save as the specified filename/location each time | 1 | 1.3
2 Back-end System | 23.1 | 30.03
2.1 Team organization | 15 | 19.5
2.1.1 Team class | 9 | 11.7
2.1.1.1 Add Person instances | 2 | 2.6
2.1.1.2 Remove Person instances | 3 | 3.9
2.1.1.3 Provide Total Team Effort | 2 | 2.6
2.1.1.4 Provide Team Effort for given EffortType | 2 | 2.6
2.1.2 Person abstract class | 2 | 2.6
2.1.2.1 Report Effort to ProjectEffort | 2 | 2.6
2.1.3 Programmer class | 2 | 2.6
2.1.3.1 Promote to Manager | 2 | 2.6
2.1.4 Manager class | 2 | 2.6
2.4.1.1 Demote to Programmer | 2 | 2.6
2.2 Effort Monitoring and Tracking System | 6.1 | 7.93
2.2.1 ProjectEffort class | 5 | 6.5
2.2.1.1 Stores all Effort instances for the project | 3 | 3.9
2.2.1.2 Can provide List<Effort> of | 2 | 2.6
2.2.2 Effort class | 1 | 1.3
2.2.3 EffortType enum | 0.1 | 0.13
2.3 Load/Save Status | 2 | 2.6
TOTAL | 76.1 | 98.93